## Meeting Logs
Date | Location | Members | Things Discussed
2018-10-05 | In Lab | All | Initial research, decided to continue to with pygame and to use pymunk as a physics engine
2018-10-10 | In Class | All | Created initial class diagrams, started planning for frontend and backend
2018-10-12 | In Class | All | UML diagrams finished, planned building prototype over weekend
2018-10-15 | Leep2 | Zach, Jacob, Gage | Discussed prototype, planned gravity implementation, general planning for next steps
2018-10-16 | Leep2 | All | Added SAS for directional control, added menu, implemented fuel, created static graphics class
2018-10-17 | In Class | Zach, Jacob, Gage | Discussed gravity further, planned automated SAS, HUD, visual effects
2018-10-19 | In Class | All | Planned finishing documentation for code stop date, final deliverables for project 3
2018-10-24 | In Class | Zach, Jacob, Gage | Discussed project 4 plan
2018-10-26 | In Class | Zach, Gage | Talked about how drawer would be implemented
2018-10-29 | Leep2 | All | Quick touch-base with each other's progress
2018-10-31 |  | Zach, Gage | Updates on drawer, use of textures and sprites and the rocket builder
2018-11-03 | Leep2 | Zach, Gage, Jacob, Thomas (Later) | Workday: Work on graphics and menu components, zooming, and trajectory calculation
2018-11-07 | In Class | Zach, Gage, Jacob | Updates and planning for frontend-backend work on rocket builder, talking of refactoring some components
2018-11-09 | In Class | Zach, Gage, Jacob | Planned to meet this weekend to work, otherwise talked about colissions, fixing of components and using interfaces for them
2018-11-10 | Leep2 | Zach, Gage, Jacob | Workday: Testing textures and zoom, refactoring of rocket components, menu designing and interfaces for components
2018-11-12 | Leep2 | Zach, Gage | Worked out meeting logs
2018-11-13 | Leep2 | Gage, Jacob | More progress on rocket builder, and more restructuring of the thruster class for better subclassing
2018-11-14 | In Class | Zach, Gage, Jacob | set code stop day Wed before thanksgiving
2018-11-16 | Leep2 | Zach, Gage | rocket builder -- drag and drop
2018-11-19 | In Class | Zach, Gage | Discussed meeting plans over break, testing and documentation
2018-11-23 | Leep2 | Zach, Gage | Set up autodocumentation, began documenting classes
2018-11-24 | Remote | All | Finished most documentation, made performance upgrades and did some refactoring
2018-11-25 | Remote | All | Finished documentation, wrote tests, tied up loose ends